## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
0 | 05/08 - 05/15 | 1.Team formation: Decided Leads for the each role and identified individual tech stack and interest. 2.Weekly meetings : Till now we have conducted three meetings and and discussed the requirment and the timeline 3.Braimstorming featurs and requirment: Team researched about existing project management system and came up with the initial overall implementation. 4.Management plan: We are dividing our work in 3 major team where initally one team would setup spring boot, team two would setup CI/CD pipeline, team 3 will work on basic database setup that we would use it. 5.TiImeline: Created initial draft for future iteration 6.Presentation: Dipayan and Pranjal worked on the presentation 7.Documentation: Created inital documentation for SPPP, SDD, Risk Managment | 1.Github issue - Some of the team members are not familiar with Git hence it is a chalenge 2. We had issue deciding project scope and what all features we wanted to implement | 1.Need to assign specific task to members. 2.There might be some conflicts due to time differtence 3.Some team member dont have enough knowledge on especific stacks | 1.Streamline requirments 2.Detaled documents and clear ideas 3.Improved comunication and cordination among team members. | 0 | 2 | 0 | 0 | 0 | 56 | Dipayan-13 Aman-13 Pranjal-15 Mukul-9 Praveen-19 | 3 | 12.5 | 7.5 | 7 | 5 | 0 | 9 | 5 | 7
1 | 05/16 - 05/28
2 | 05/29 - 06/11
3 | 06/12 - 06/18

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Dipayan | Initializing and Proof reading | Initializing and Proof reading | Initializing and Proof reading

## Pranjal Ekhande
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/8-05/16 | 15 | 12 | 3 | 0 - Learnt Git pipelining 1 - Discussion and research 2 - Architectural Planning 5 - Setting up meeting with the team 6 - Setting Up of Git Group. 7 - Project documentation SPP | 1 | 2.5 | 1 |  |  | 0.5 | 1 | 6 | 1. Wrote Majority of SPPP documentation. 2. Setup git. 3. Presentation Participation in iteration 0. 4. Work on documentation | 1. There was lot of confusion in team. We struggled with defining tasks. Goal defined by our team was overlapping with other team. 2. Teammate including myself had a travel plans and final exams |  | 1. Set up spring setup 2. Design basic database 3. Define User roles for project management | 15

## Mukul Jangid
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9 | 6 | 3 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Aman Jain
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 05/08- 05/16 | 13 | 10 | 3 | 0- Learning git, Pivotal 1 - Discussion and research 5 - team meetings 6- set up git | 3.5 | 2 | 1 |  |  | 1 | 2 | 0.5 | 1. Work on documtations 2. Set up Git 3. Participate in presentation | 1. Not fimiliar with pivotal 2. revisiing springboot, not fimiliar with intellij IDE and STS 2.due to travel plan lack of communications | 1. Learninig sprinboot CFL and STS and IDE tools in 2 weeks 2.Working on progess report | 1. Contine to learn Springboot, GIt and Pivotal 2. need to setup CI/CD pipeline | 10

## Dipayan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 13 | 10 | 3 | 0 - Learn Git/ Setup 2 - Designing the initial Documentation 5 - Presentation 5 - Meetings 3 - Worked on iteration 0 | 1 |  | 4 | 1 |  | 4 |  |  | 1. Created the first draft of SPPP, STD etc 2. Presented for iteration 0 | 1. Learning GIT has a learning curve to it | 1. GIT setup is complete | 1. Complete the initial requirements of the documentations | 10

## Praveen Singh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 16.5 | 14.5 | 2 | 0 - learn git and FE implementation 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 5 | 3 | 2 |  |  | 3 | 1 | 0.5 | 1. Discussing project idea and how to implement 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Deciding the project topic | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn FE 1 - continue to define requirements 2 - implement the login page | 8
2 | 05/8-05/16 | 19 | 16 | 3 | 0 - Implement FE 1 - Design the login screen 2 - make project plan 3 - prepare presentation 4 - database connection | 4 | 2 | 2 | 4 |  | 3 | 1 |  | 1. Designing the user login screen | 1. Implementing the database |  | 0 - continue to learn FE and make connections with the database 1 - Implementing the BE | 12