## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | New member(s) join the team | 3 | 4 | 4 | 24 | team leader and all members |  | Brief the new member(s) about the scope requirements. If they're unable to take on the responsibilities, reassign and triage new responsibilities among the team | No new additions in team
| Lack of motivation or responsibility | Team members aren't dedicated towards their tasks or aren't willing to take new responsibilities. | 3 | 4 | 4 | 24 | team leader and all members |  | Have regular meetings with team members for updates. Explain the team members the impact of their contribution. If they know their significance, they'll understand the importance of their tasks completion. | Hasn't been an issue now since the work is just being initialized now. It might be implemented later in upcoming weeks.
Communication | duplicate work | Lack of communication can cause team members to work on the same task. This leads to a task taking double time and another task not being picked. | 2 | 4 | 3 | 24 | team leader and all members |  | Each member will inform about the tasks that they're working on and which tasks they'll pick up next. This ensures that each member knows about other's current and future tasks. | Tasks are being created and assigned to members on pivotal tracker.
| worked on wrong components | Lack of communication can cause team members to work on task that weren't assigned to them, thus they are working on other's tasks. | 2 | 3 | 3 | 36 | team leader and all members |  | Every team member will inform about the tasks that they're working on. This ensures that each member knows about other's current tasks. | Team members are making sure to pick up only those tasks that are assigned to them.
| useless work | Team members focusing too much on inconsequential tasks. | 3 | 2 | 1 | 12 | team leader and all members |  | Every team member will make sure they triage their tasks appropriately. | Hasn't been an issue now since tasks are being created. It might be implemented later in upcoming weeks.
| inconsistent work | Team members do not push their work and rebase their work regularly. | 3 | 2 | 2 | 24 | team leader and all members |  | Every team member will make sure they commit and push their changes regularly. Before starting with new task, they will make sure that they're on the latest version of the branch. | Hasn't been an issue now since we're still in planning phase.
Requirements | unclear requirements | Lack of task clarity can cause team members to do work that's incorrect or doesn't correspond to task description | 2 | 3 | 3 | 36 | Requirement Leader |  | Every team member will make sure they completely understand the task description and Requirement Leader should be careful about the same. | Hasn't been an issue now since tasks are being created.
| scope creep | Team members continuously expand or modify the project scope without proper procedure and documentation | 2 | 3 | 2 | 24 | Requirement Leader |  | Requirement Leader will regularly review and discuss the project scope and ensure any changes are documented and communicated to all team members. | Hasn't been an issue now since tasks are being created.
| constant requirements changes | Team members continuously modify the project scope without proper need. An example being, changing API payload or response as per individual's convenience | 3 | 3 | 3 | 27 | Requirement Leader |  | Requirement Leader will set a proper procedure for requirement changes and ensure that all the changes are communicated and documented. | Hasn't been an issue now since tasks are being created.
Management | improper task assignments | Tasks are not assigned according to team member's strengths and availability. | 2 | 3 | 3 | 36 | team leader |  | Team leader will review team member strengths and availability before assigning new tasks. Team leader will also keep an eye on progress of the team and redistribute tasks accordingly as needed. | Leads are assigned after proper discussion about their strengths.
| improper planning | Lack of proper planning that will lead to missing deadlines and poor work quality. | 3 | 4 | 3 | 18 | team leader |  | Team leader will develop a detailed project plan with milestones and deadlines. TL will also regularly review and adjust the plans as needed. | Initial planning is done, regular reviews are ongoing.
| lack of management skills | Ineffective management leading to team inefficiency and low morale. | 2 | 3 | 2 | 24 | team leader |  | Team leader will provide management training and resources for the team. TL will also gathere feedback regularly from the team to improve management practices. | No issues currently; monitoring and feedback collection are ongoing.
Technology competence | Not familiar with the framework used | Team members are not familiar with the framework required for the project. | 4 | 3 | 3 | 18 | Design & Implementation leader |  | Team members will learn and try hands on approach before starting with the tasks. DI leader will provide guidance on resources to learn about the framework. DIL will pair less experienced members with experienced ones. | Initial training provided, ongoing support available.
| Not familiar with the programming language used | Team members are not familiar with the programming language required for the project. | 3 | 4 | 3 | 18 | Design & Implementation leader |  | DI leader will provide training and resources for the programming language. DIL will pair less experienced members with experienced ones. | Initial training provided, ongoing support available.
| Not familiar with unit testing | Team members are not familiar with writing, executing and standards of unit tests. | 3 | 3 | 3 | 27 | Design & Implementation leader and Security Leader |  | DI leader will provide training and resources for unit testing. DIL will educate and SL will set standards for unit testing. | Initial training provided, ongoing support available.
| Other technology incompetence | Team members lack skills in other required technologies. | 3 | 3 | 3 | 27 | Design & Implementation leader and Configuration Leader |  | DI leader and Configuration Leader will provide training and resources for unit testing along with setting standards for unit testing. DIL will pair less experienced members with experienced ones. | Initial training provided, ongoing support available.
| Not familiar with Git | Team members are not familiar with using Git for version control. | 3 | 3 | 3 | 27 | Configuration Leader |  | CL will provide training and resources for Git. CL will also provide guidance when members are stuck with problems like merge conflicts. | Initial training provided, ongoing support available.
Design and implementation | Improper design | The design of the project is flawed, leading to issues in implementation and integration. | 4 | 4 | 4 | 16 | Design & Implementation leader |  | DI leader will review design regularly and validation against requirements. DIL will also adjust design based on feedback and testing results. | Planning and reviewing initial design.
| improper technology stack | The chosen technology stack is not suitable for the project requirements. | 4 | 4 | 4 | 16 | Design & Implementation leader |  | DI leader will review and validate the chosen technology stack. DIL will be open to changing components if they do not meet project needs. | Planning and reviewing initial stack.
| Messy code | Poorly written and unorganized code leading to difficulties in maintenance and scaling. | 4 | 3 | 3 | 18 | Design & Implementation leader and Configuration Leader |  | DI leader will implement coding standards and perform regular code reviews. DIL will ensure that members are documenting code and suggest refactoring as needed. CL will provide guidance on setting up tools like linters so that the codebase follows contemporary code conventions. | Coding standards established. CL will finalize and setup tools.
Testing | Not enough testing | Inadequate testing leading to undiscovered bugs and issues in the final product. | 4 | 4 | 3 | 12 | Security Leader and QA Leader |  | SL and QAL will develop a comprehensive testing plan covering unit, integration, and system tests. They will allocate sufficient time for testing in the project schedule. | Planning and reviewing initial testing plan.
Integration and deployment | Not enough time for integration and deployment | Insufficient time allocated for integrating and deploying the final product. | 4 | 3 | 3 | 18 | Design & Implementation leader |  | DIL will ensure the project plan includes adequate time for integration and deployment. | Initial schedule includes integration and deployment time.
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.